## Product_Backlog
ID | As a /an | I want to | so that | Priority | Sprint Point | Status | Assignee
1 | Web-App Developer | know the project definition and scope | I can design the database | High | 5 | Complete | Scrum Team
2 | Web-App Developer | normalize the database tables | the data is stored appropriately | High | 3 | Complete | Scrum Team
3 | User | Register myself | I can provide my details for the future purchase | High | 3 | Complete | Arun Sharma
4 | User | Login myself | I can access my account and see order details | High | 2 | Complete | Arun Sharma
5 | User | Have functionality of forgot password | I can change my password and reset it | High | 3 | In progress | Arun Sharma
6 | User | Edit and View my profile | I can change my account details | Medium | 5 | In progress | Arun Sharma
7 | User | Change password | I can change my password in my profile | Medium | 2 | In progress | Arun Sharma
8 | User | View homepage and products | I can view variety of products at once and understand the navigation of the website | High | 8 | Incomplete | Krishna Shah
9 | User | View products according to the category | I can view all the products in a particular category | Low | 5 | Incomplete | Krishna Shah
10 | User | Search products | its easy to find products I need | Low | 3 | Incomplete | Krishna Shah
11 | User | Customize product | I can get them designed according to my needs | High | 8 | Incomplete | Uma Ranawat
12 | User | Order Products | I can purchase products | High | 5 | Incomplete | Kashyap Patel
13 | User | Add to cart | I can collect product I wish to buy | High | 3 | Incomplete | Harsh Mistry
14 | User | Manage cart | I can add update delete products | Medium | 3 | Incomplete | Harsh Mistry
15 | User | View my Order before proceeding to check out | I can confirm my order with its total price | High | 2 | Incomplete | Kashyap Patel
16 | Admin | Login myself | I can login to admin panel | High | 8 | Incomplete | Uma Ranawat
17 | Admin | View and manage category | I can view ,add,update and delete Categories | Medium | 5 | Incomplete | Uma Ranawat
18 | Admin | Search products by product name | I can view particular products and their details | Low | 3 | Incomplete | Harsh Mistry
19 | Admin | Manage products | I can add, update and delete products and their details | Medium | 5 | Incomplete | Krishna Shah
20 | Admin | Manage products' stock | I can update stocks of different products | High | 3 | Incomplete | Uma Ranawat
21 | Admin | View and manage customized orders | I can keep track of customized orders | High | 5 | Incomplete | Kashyap Patel
22 | Admin | View orders and their summary | I can keep track of all the orders | Medium | 5 | Incomplete | Kashyap Patel
23 | Admin | Verify user emails | I can have genuine data | Medium | 3 | Complete | Arun Sharma

## Sprint-1
Sprint-1
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Sprint Review
As a/An Web-app Developer I want to know the project definition and scope so that I can design the database. | Understand the project definition and scope well | Uma Ranawat, Arun Sharma, Krishna Shah, Harsh Mistry , Kashyap Patel | Completed | 15 | 7 | 3 | 3 | 3 | 0 | 0 | 0
| Determine the tables | Uma Ranawat, Arun Sharma, Krishna Shah, Harsh Mistry , Kashyap Patel | Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0
As a/an Web-app Developer I want to normalize the table so that the data is store appropriately | Analyse the tables | Uma Ranawat, Krishna Shah, Harsh Mistry | Completed | 3 | 0 | 1 | 2 | 0 | 0 | 0 | 0
| Normalize the tables | Uma Ranawat, Krishna Shah | Completed | 3 | 0 | 0 | 0 | 2 | 1 | 0 | 0
| Prepare the Database | Uma Ranawat, Arun Sharma | Completed | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0
| Total |  |  | 28 | 9 | 6 | 6 | 5 | 3 | 0 | 0

## Sprint-2
Sprint-2
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Sprint Review
As a/An User I want to register myself so that I can provide my details for the future purchase. | Design the register form | Uma Ranawat | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| Validate the form | Uma Ranawat | Completed | 6 | 1 | 4 | 3 | 0 | 0 | 0 | 0
| Code the logic to register the user according to type | Arun Sharma | Completed | 7 | 0 | 2 | 3 | 3 | 1 | 0
| Run the tests | Krishna Shah | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 1
As a/an User I want to login myself so that I can access my account and see order details. | Design the login form. | Uma Ranawat | Completed | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0
| Code the logic to login the user according to type | Arun Sharma | Completed | 3 | 0 | 0 | 0 | 2 | 1 | 0 | 0
| Run the tests | Krishna Shah | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
| Total |  |  | 25 | 5 | 8 | 7 | 5 | 3 | 1 | 0

## Sprint-3
Sprint-3
Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Sprint Review
As a/An User I want to have functionality of forgot password so that I canI can change my password and reset it through email | Design the page for forget password | Uma Ranawat | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Code the logic to check the email id is registered or not | Arun Sharma | Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0
| Run the tests | Arun Sharma | Completed | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| Design the format of email | Krishna Shah | Completed | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0
| Code the logic to send the email | Arun Sharma | Completed | 6 | 0 | 0 | 2 | 3 | 1 | 0 | 0
| Run the tests | Arun Sharma | Completed | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0
As a/an Admin I want to verify user emails so that I can have genuine data. | Design the verification UI | Uma Ranawat | Completed | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
| Code the logic to verify the email of the user logged in. | Arun Sharma | Completed | 4 | 0 | 0 | 0 | 0 | 3 | 0 | 0
| Run the tests | Arun Sharma | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0
| Total |  |  | 23 | 4 | 3 | 6 | 3 | 5 | 1 | 0